## Project
No | Category | No | Project | Project Code | Category
1 | Web Development | 1 | Teeb Product Demonstration | TEEBPD | Web Development
2 | Software Development | 2 | Ticketing | TKT | Web Development
|  | 3 | Sending Data to the site | SDS | Software Development
|  | 4 | Replication Tool Modification | RTM | Software Development
|  | 5 | Paper Point Online and Inhouse Ordering | PPOIO | Web Development
|  | 6 | Appframe | APPFRAME | Web Development
|  | 7 | Milestone Website | MITWEB | Web Development

## Tasks
No | Project | PRJTSKSEQ | Task | TaskProjectCode | PRJ | TSK
1 | TEEBPD | TEEBPD-1 | Theme Designing | TEEBPD/Theme Designing | TEEBPD | Theme Designing
2 | TEEBPD | TEEBPD-2 | Database Structure Designing | TEEBPD/Database Structure Designing | TEEBPD | Database Structure Designing
3 | TEEBPD | TEEBPD-3 | Appframe configuration | TEEBPD/Appframe configuration | TEEBPD | Appframe configuration
4 | TEEBPD | TEEBPD-4 | Inhouse Testing | TEEBPD/Inhouse Testing | TEEBPD | Inhouse Testing
5 | TEEBPD | TEEBPD-5 | Client Demonstration | TEEBPD/Client Demonstration | TEEBPD | Client Demonstration
6 | TEEBPD | TEEBPD-6 | Client Suggestion Implementation | TEEBPD/Client Suggestion Implementation | TEEBPD | Client Suggestion Implementation
7 | TKT | TKT-1 | Database Analysis from Old Project | TKT/Database Analysis from Old Project | TKT | Database Analysis from Old Project
8 | TKT | TKT-2 | DB Designing | TKT/DB Designing | TKT | DB Designing
9 | TKT | TKT-3 | Appframe configuration | TKT/Appframe configuration | TKT | Appframe configuration
10 | TKT | TKT-4 | Discussion for ticketing modification | TKT/Discussion for ticketing modification | TKT | Discussion for ticketing modification
11 | SDS | SDS-1 | Decryption | SDS/Decryption | SDS | Decryption
12 | RTM | RTM-1 | Solving the issue of repeating icon in tray | RTM/Solving the issue of repeating icon in tray | RTM | Solving the issue of repeating icon in tray
13 | PPOIO | PPOIO-1 | Project Study | PPOIO/Project Study | PPOIO | Project Study
14 | PPOIO | PPOIO-2 | Business Plan | PPOIO/Business Plan | PPOIO | Business Plan
15 | APPFRAME | APPFRAME-1 | Development | APPFRAME/Development | APPFRAME | Development
16 | MITWEB | MITWEB-1 | Modification | MITWEB/Modification | MITWEB | Modification
17 | RTM | RTM-2 | Getting branchname into tool | RTM/Getting branchname into tool | RTM | Getting branchname into tool
18 | TKT | TKT-5 | Note down table relations | TKT/Note down table relations | TKT | Note down table relations
19 | TKT | TKT-6 | Entering table details into excel sheet | TKT/Entering table details into excel sheet | TKT | Entering table details into excel sheet
20 | SDS | SDS-2 | Request and get Response from web | SDS/Request and get Response from web | SDS | Request and get Response from web

## Employees
No | Name
1 | Aswathy
2 | Vishnu
3 | Shareena
4 | Firose

## Task Timings
No | PRJ | TSK | EmployeeDate | EmployeeDateSeq | EmployeeDateSeqCode | Task | Employee | Date | Start Time | End Time | Total Minutes | Total | Day Total Minutes | Day Total | PRJLST | TSKLST
1 | TKT | Discussion for ticketing modification | Aswathy/43430 | 1 | Aswathy/43430/1 | TKT/Discussion for ticketing modification | Aswathy | 2018-11-26 | 9:30 | 11:00 | 90 | 01:30 | 330 | 05:30 | TKT | Discussion for ticketing modification
2 | TKT | Discussion for ticketing modification | Shareena/43430 | 1 | Shareena/43430/1 | TKT/Discussion for ticketing modification | Shareena | 2018-11-26 | 9:30 | 11:00 | 90 | 01:30 | 331 | 05:31 | TKT | Discussion for ticketing modification
3 | SDS | Decryption | Aswathy/43430 | 2 | Aswathy/43430/2 | SDS/Decryption | Aswathy | 2018-11-26 | 11:00 | 11:30 | 30 | 00:30 | 330 | 05:30 | SDS | Decryption
4 | TKT | Database Analysis from Old Project | Shareena/43430 | 2 | Shareena/43430/2 | TKT/Database Analysis from Old Project | Shareena | 2018-11-26 | 11:25 | 13:26 | 121 | 02:01 | 331 | 05:31 | TKT | Database Analysis from Old Project
5 | RTM | Solving the issue of repeating icon in tray | Aswathy/43430 | 3 | Aswathy/43430/3 | RTM/Solving the issue of repeating icon in tray | Aswathy | 2018-11-26 | 11:30 | 13:00 | 90 | 01:30 | 330 | 05:30 | RTM | Solving the issue of repeating icon in tray
6 | TKT | Database Analysis from Old Project | Shareena/43430 | 3 | Shareena/43430/3 | TKT/Database Analysis from Old Project | Shareena | 2018-11-26 | 14:00 | 16:00 | 120 | 02:00 | 331 | 05:31 | TKT | Database Analysis from Old Project
7 | RTM | Solving the issue of repeating icon in tray | Aswathy/43430 | 4 | Aswathy/43430/4 | RTM/Solving the issue of repeating icon in tray | Aswathy | 2018-11-26 | 15:00 | 17:00 | 120 | 02:00 | 330 | 05:30 | RTM | Solving the issue of repeating icon in tray
8 | TKT | Discussion for ticketing modification | Firose/43430 | 1 | Firose/43430/1 | TKT/Discussion for ticketing modification | Firose | 2018-11-26 | 10:00 | 11:00 | 60 | 01:00 | 420 | 07:00 | TKT | Discussion for ticketing modification
9 | PPOIO | Project Study | Firose/43430 | 2 | Firose/43430/2 | PPOIO/Project Study | Firose | 2018-11-26 | 11:00 | 13:00 | 120 | 02:00 | 420 | 07:00 | PPOIO | Project Study
10 | PPOIO | Business Plan | Firose/43430 | 3 | Firose/43430/3 | PPOIO/Business Plan | Firose | 2018-11-26 | 14:00 | 18:00 | 240 | 04:00 | 420 | 07:00 | PPOIO | Business Plan
11 | TEEBPD | Client Suggestion Implementation | Firose/43431 | 1 | Firose/43431/1 | TEEBPD/Client Suggestion Implementation | Firose | 2018-11-27 | 9:00 | 17:00 | 480 | 08:00 | 480 | 08:00 | TEEBPD | Client Suggestion Implementation
12 | TKT | Database Analysis from Old Project | Shareena/43431 | 1 | Shareena/43431/1 | TKT/Database Analysis from Old Project | Shareena | 2018-11-27 | 9:15 | 11:30 | 135 | 02:15 | 135 | 02:15 | TKT | Database Analysis from Old Project
13 | RTM | Solving the issue of repeating icon in tray | Aswathy/43431 | 1 | Aswathy/43431/1 | RTM/Solving the issue of repeating icon in tray | Aswathy | 2018-11-27 | 9:15 | 10:00 | 45 | 00:45 | 145 | 02:25 | RTM | Solving the issue of repeating icon in tray
12 | RTM | Solving the issue of repeating icon in tray | Aswathy/43431 | 2 | Aswathy/43431/2 | RTM/Solving the issue of repeating icon in tray | Aswathy | 2018-11-27 | 11:20 | 13:00 | 100 | 01:40 | 145 | 02:25 | RTM | Solving the issue of repeating icon in tray
12 | MITWEB | Modification | Firose/43432 | 1 | Firose/43432/1 | MITWEB/Modification | Firose | 2018-11-28 | 9:00 | 10:00 | 60 | 01:00 | 90 | 01:30 | MITWEB | Modification
13 | TKT | Discussion for ticketing modification | Firose/43432 | 2 | Firose/43432/2 | TKT/Discussion for ticketing modification | Firose | 2018-11-28 | 10:00 | 10:30 | 30 | 00:30 | 90 | 01:30 | TKT | Discussion for ticketing modification
14 | TKT | Note down table relations | Shareena/43432 | 1 | Shareena/43432/1 | TKT/Note down table relations | Shareena | 2018-11-28 | 10:32 | 16:52 | 380 | 06:20 | 380 | 06:20 | TKT | Note down table relations
15 | SDS | Decryption | Aswathy/43432 | 1 | Aswathy/43432/1 | SDS/Decryption | Aswathy | 2018-11-28 | 10:35 | 11:45 | 70 | 01:10 | 320 | 05:20 | SDS | Decryption
16 | RTM | Getting branchname into tool | Aswathy/43432 | 2 | Aswathy/43432/2 | RTM/Getting branchname into tool | Aswathy | 2018-11-28 | 12:15 | 12:45 | 30 | 00:30 | 320 | 05:20 | RTM | Getting branchname into tool
17 | SDS | Decryption | Aswathy/43432 | 3 | Aswathy/43432/3 | SDS/Decryption | Aswathy | 2018-11-28 | 12:45 | 16:25 | 220 | 03:40 | 320 | 05:20 | SDS | Decryption
18 | TKT | Note down table relations | Shareena/43433 | 1 | Shareena/43433/1 | TKT/Note down table relations | Shareena | 2018-11-29 | 11:05 | 13:15 | 130 | 02:10 | 250 | 04:10 | TKT | Note down table relations
19 | TKT | Entering table details into excel sheet | Shareena/43433 | 2 | Shareena/43433/2 | TKT/Entering table details into excel sheet | Shareena | 2018-11-29 | 13:45 | 15:45 | 120 | 02:00 | 250 | 04:10 | TKT | Entering table details into excel sheet
20 | SDS | Request and get Response from web | Aswathy/43434 | 1 | Aswathy/43434/1 | SDS/Request and get Response from web | Aswathy | 2018-11-30 | 9:20 | 13:08 | 228 | 03:48 | 228 | 03:48 | SDS | Request and get Response from web
21 | TKT | Entering table details into excel sheet | Shareena/43434 | 1 | Shareena/43434/1 | TKT/Entering table details into excel sheet | Shareena | 2018-11-30 | 9:45 | 13:10 | 205 | 03:25 | 205 | 03:25 | TKT | Entering table details into excel sheet

## Project Report
Sending Data to the site
Employee Wise Timing
SDS |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Seq | Tasks |  | Total Time | Aswathy | Vishnu | Shareena | Firose
1 | Decryption |  | 320 | 320 | 0 | 0 | 0 | 0 | 0 | 0
2 | Request and get Response from web |  | 228 | 228 | 0 | 0 | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 548 | 548 | 0 | 0 | 0 | 0 | 0 | 0

## Employee Timing Report
Aswathy |  |  | Start Date |  | Minutes | Hours
|  |  | 2018-11-26 |  | 1023 | 17:03
Project Wise Timing
6 Day Report
1 | [6 empty] | No | Project |  | Minutes
2 | 2018-11-26 | TKT/Discussion for ticketing modification |  | 90 | 330 |  | 1 | TKT |  | 0 |  |  | 1 | TKT | 1 | 1 | TKT | TKT/1 | Discussion for ticketing modification | 90
3 |  | SDS/Decryption |  | 30 |  |  | 2 | SDS |  | 548 |  |  | 1 | SDS | 1 | 2 | SDS | SDS/1 | Decryption | 320
4 |  | RTM/Solving the issue of repeating icon in tray |  | 90 |  |  | 3 |  |  | 0 |  |  | 1 | RTM | 1 | 4 | RTM | RTM/1 | Solving the issue of repeating icon in tray | 355
1 |  | RTM/Solving the issue of repeating icon in tray |  | 120 |  |  | 4 | RTM |  | 385 |  |  | 0 | [6 empty] | 0
2 | 2018-11-27 | RTM/Solving the issue of repeating icon in tray |  | 45 | 145 |  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0
3 |  | RTM/Solving the issue of repeating icon in tray |  | 100 | [8 empty] | 0 | [6 empty] | 0
4 |  |  |  | 0 |  |  | Project Task Wise Timing | [5 empty] | 0 | [6 empty] | 0
1 |  |  |  | 0 | [8 empty] | 0 | [6 empty] | 0
2 | 2018-11-28 | SDS/Decryption |  | 70 | 320 |  | Project |  | Tasks |  | Task Time | Total | 0 | [6 empty] | 0
3 |  | RTM/Getting branchname into tool |  | 30 |  | 1 | TKT |  | Discussion for ticketing modification |  | 90 | 90 | 1 | RTM | 2 |  | RTM | RTM/2 | Getting branchname into tool | 30
4 |  | SDS/Decryption |  | 220 |  | 2 | [6 empty] | 0 | [6 empty] | 0
1 |  |  |  | 0 |  | 3 | [6 empty] | 0 | [6 empty] | 0
2 | 2018-11-29 |  |  | 0 | 0 | 4 | [6 empty] | 0 | [6 empty] | 0
3 |  |  |  | 0 |  | 1 | SDS |  | Decryption |  | 320 | 548 | 0 | [6 empty] | 0
4 |  |  |  | 0 |  | 2 |  |  | Request and get Response from web |  | 228 |  | 0 | [6 empty] | 0
1 |  |  |  | 0 |  | 3 | [6 empty] | 0 | [6 empty] | 0
2 | 2018-11-30 | SDS/Request and get Response from web |  | 228 | 228 | 4 | [6 empty] | 1 | SDS | 2 |  | SDS | SDS/2 | Request and get Response from web | 228
3 |  |  |  | 0 |  | 1 | [5 empty] | 0 | 0 | [6 empty] | 0
4 |  |  |  | 0 |  | 2 | [6 empty] | 0 | [6 empty] | 0
1 |  |  |  | 0 |  | 3 | [6 empty] | 0 | [6 empty] | 0
2 | 2018-12-01 |  |  | 0 | 0 | 4 | [6 empty] | 0 | [6 empty] | 0
3 |  |  |  | 0 |  | 1 | RTM |  | Solving the issue of repeating icon in tray |  | 355 | 385 | 0 | [6 empty] | 0
4 |  |  |  | 0 |  | 2 |  |  | Getting branchname into tool |  | 30 |  | 0 | [6 empty] | 0
|  |  |  | 0 |  | 3 | [6 empty] | 0 | [6 empty] | 0
4
[6 empty] | 1 | [5 empty] | 0
2
3
4