## Project
No | Category | No | Project | Project Code | Category
1 | Web Development | 1 | Teeb Product Demonstration | TEEBPD | Web Development
2 | Software Development | 2 | Ticketing | TKT | Web Development
|  | 3 | Sending Data to the site | SDS | Software Development
|  | 4 | Replication Tool Modification | RTM | Software Development
|  | 5 | Paper Point Online and Inhouse Ordering | PPOIO | Web Development
|  | 6 | Appframe | APPFRAME | Web Development
|  | 7 | Milestone Website | MITWEB | Web Development
|  | 8 | AMC Request | AMC | Software Development
|  | 9 | Restore Database | RTRDB | Software Development

## Tasks
No | Project | PRJTSKSEQ | Task | TaskProjectCode | PRJ | TSK
1 | TEEBPD | TEEBPD-1 | Theme Designing | TEEBPD/Theme Designing | TEEBPD | Theme Designing
2 | TEEBPD | TEEBPD-2 | Database Structure Designing | TEEBPD/Database Structure Designing | TEEBPD | Database Structure Designing
3 | TEEBPD | TEEBPD-3 | Appframe configuration | TEEBPD/Appframe configuration | TEEBPD | Appframe configuration
4 | TEEBPD | TEEBPD-4 | Inhouse Testing | TEEBPD/Inhouse Testing | TEEBPD | Inhouse Testing
5 | TEEBPD | TEEBPD-5 | Client Demonstration | TEEBPD/Client Demonstration | TEEBPD | Client Demonstration
6 | TEEBPD | TEEBPD-6 | Client Suggestion Implementation | TEEBPD/Client Suggestion Implementation | TEEBPD | Client Suggestion Implementation
7 | TKT | TKT-1 | Database Analysis from Old Project | TKT/Database Analysis from Old Project | TKT | Database Analysis from Old Project
8 | TKT | TKT-2 | DB Designing | TKT/DB Designing | TKT | DB Designing
9 | TKT | TKT-3 | Appframe configuration | TKT/Appframe configuration | TKT | Appframe configuration
10 | TKT | TKT-4 | Discussion for ticketing modification | TKT/Discussion for ticketing modification | TKT | Discussion for ticketing modification
11 | SDS | SDS-1 | Decryption | SDS/Decryption | SDS | Decryption
12 | RTM | RTM-1 | Solving the issue of repeating icon in tray | RTM/Solving the issue of repeating icon in tray | RTM | Solving the issue of repeating icon in tray
13 | PPOIO | PPOIO-1 | Project Study | PPOIO/Project Study | PPOIO | Project Study
14 | PPOIO | PPOIO-2 | Business Plan | PPOIO/Business Plan | PPOIO | Business Plan
15 | APPFRAME | APPFRAME-1 | Development | APPFRAME/Development | APPFRAME | Development
16 | MITWEB | MITWEB-1 | Modification | MITWEB/Modification | MITWEB | Modification
17 | RTM | RTM-2 | Getting branchname into tool | RTM/Getting branchname into tool | RTM | Getting branchname into tool
18 | TKT | TKT-5 | Note down table relations | TKT/Note down table relations | TKT | Note down table relations
19 | TKT | TKT-6 | Entering table details into excel sheet | TKT/Entering table details into excel sheet | TKT | Entering table details into excel sheet
20 | SDS | SDS-2 | Request and get Response from web | SDS/Request and get Response from web | SDS | Request and get Response from web
21 | TEEBPD | TEEBPD-7 | Finalizing | TEEBPD/Finalizing | TEEBPD | Finalizing
22 | SDS | SDS-3 | Testing | SDS/Testing | SDS | Testing
23 | SDS | SDS-4 | Stage 2 | SDS/Stage 2 | SDS | Stage 2
24 | TEEBPD | TEEBPD-8 | Synchronization Implementing | TEEBPD/Synchronization Implementing | TEEBPD | Synchronization Implementing
25 | TKT | TKT-7 | Package Creation-Stage1 | TKT/Package Creation-Stage1 | TKT | Package Creation-Stage1
26 | SDS | SDS-5 | Modification | SDS/Modification | SDS | Modification
27 | TKT | TKT-8 | Package Creation-Stage2(Resource creation) | TKT/Package Creation-Stage2(Resource creation) | TKT | Package Creation-Stage2(Resource creation)
28 | TEEBPD | TEEBPD-9 | Table syncing | TEEBPD/Table syncing | TEEBPD | Table syncing
29 | RTM | RTM-3 | Modification | RTM/Modification | RTM | Modification
30 | SDS | SDS-6 | Error Correction | SDS/Error Correction | SDS | Error Correction
31 | AMC | AMC-1 | Documentation | AMC/Documentation | AMC | Documentation
32 | RTRDB | RTRDB-1 | Documentation | RTRDB/Documentation | RTRDB | Documentation
33 | RTRDB | RTRDB-2 | Surrender PC | RTRDB/Surrender PC | RTRDB | Surrender PC
34 | RTRDB | RTRDB-3 | Restore DB | RTRDB/Restore DB | RTRDB | Restore DB

## Employees
No | Name
1 | Aswathy
2 | Vishnu
3 | Shareena
4 | Firose

## Task Timings
No | PRJ | TSK | EmployeeDate | EmployeeDateSeq | EmployeeDateSeqCode | Task | Employee | Date | Start Time | End Time | Total Minutes | Total | Day Total Minutes | Day Total | PRJLST | TSKLST
1 | TKT | Discussion for ticketing modification | Aswathy/43430 | 1 | Aswathy/43430/1 | TKT/Discussion for ticketing modification | Aswathy | 2018-11-26 | 9:30 | 11:00 | 90 | 01:30 | 330 | 05:30 | TKT | Discussion for ticketing modification
2 | TKT | Discussion for ticketing modification | Shareena/43430 | 1 | Shareena/43430/1 | TKT/Discussion for ticketing modification | Shareena | 2018-11-26 | 9:30 | 11:00 | 90 | 01:30 | 331 | 05:31 | TKT | Discussion for ticketing modification
3 | SDS | Decryption | Aswathy/43430 | 2 | Aswathy/43430/2 | SDS/Decryption | Aswathy | 2018-11-26 | 11:00 | 11:30 | 30 | 00:30 | 330 | 05:30 | SDS | Decryption
4 | TKT | Database Analysis from Old Project | Shareena/43430 | 2 | Shareena/43430/2 | TKT/Database Analysis from Old Project | Shareena | 2018-11-26 | 11:25 | 13:26 | 121 | 02:01 | 331 | 05:31 | TKT | Database Analysis from Old Project
5 | RTM | Solving the issue of repeating icon in tray | Aswathy/43430 | 3 | Aswathy/43430/3 | RTM/Solving the issue of repeating icon in tray | Aswathy | 2018-11-26 | 11:30 | 13:00 | 90 | 01:30 | 330 | 05:30 | RTM | Solving the issue of repeating icon in tray
6 | TKT | Database Analysis from Old Project | Shareena/43430 | 3 | Shareena/43430/3 | TKT/Database Analysis from Old Project | Shareena | 2018-11-26 | 14:00 | 16:00 | 120 | 02:00 | 331 | 05:31 | TKT | Database Analysis from Old Project
7 | RTM | Solving the issue of repeating icon in tray | Aswathy/43430 | 4 | Aswathy/43430/4 | RTM/Solving the issue of repeating icon in tray | Aswathy | 2018-11-26 | 15:00 | 17:00 | 120 | 02:00 | 330 | 05:30 | RTM | Solving the issue of repeating icon in tray
8 | TKT | Discussion for ticketing modification | Firose/43430 | 1 | Firose/43430/1 | TKT/Discussion for ticketing modification | Firose | 2018-11-26 | 10:00 | 11:00 | 60 | 01:00 | 420 | 07:00 | TKT | Discussion for ticketing modification
9 | PPOIO | Project Study | Firose/43430 | 2 | Firose/43430/2 | PPOIO/Project Study | Firose | 2018-11-26 | 11:00 | 13:00 | 120 | 02:00 | 420 | 07:00 | PPOIO | Project Study
10 | PPOIO | Business Plan | Firose/43430 | 3 | Firose/43430/3 | PPOIO/Business Plan | Firose | 2018-11-26 | 14:00 | 18:00 | 240 | 04:00 | 420 | 07:00 | PPOIO | Business Plan
11 | TEEBPD | Client Suggestion Implementation | Firose/43431 | 1 | Firose/43431/1 | TEEBPD/Client Suggestion Implementation | Firose | 2018-11-27 | 9:00 | 17:00 | 480 | 08:00 | 480 | 08:00 | TEEBPD | Client Suggestion Implementation
12 | TKT | Database Analysis from Old Project | Shareena/43431 | 1 | Shareena/43431/1 | TKT/Database Analysis from Old Project | Shareena | 2018-11-27 | 9:15 | 11:30 | 135 | 02:15 | 135 | 02:15 | TKT | Database Analysis from Old Project
13 | RTM | Solving the issue of repeating icon in tray | Aswathy/43431 | 1 | Aswathy/43431/1 | RTM/Solving the issue of repeating icon in tray | Aswathy | 2018-11-27 | 9:15 | 10:00 | 45 | 00:45 | 145 | 02:25 | RTM | Solving the issue of repeating icon in tray
14 | RTM | Solving the issue of repeating icon in tray | Aswathy/43431 | 2 | Aswathy/43431/2 | RTM/Solving the issue of repeating icon in tray | Aswathy | 2018-11-27 | 11:20 | 13:00 | 100 | 01:40 | 145 | 02:25 | RTM | Solving the issue of repeating icon in tray
15 | MITWEB | Modification | Firose/43432 | 1 | Firose/43432/1 | MITWEB/Modification | Firose | 2018-11-28 | 9:00 | 10:00 | 60 | 01:00 | 210 | 03:30 | MITWEB | Modification
16 | TKT | Discussion for ticketing modification | Firose/43432 | 2 | Firose/43432/2 | TKT/Discussion for ticketing modification | Firose | 2018-11-28 | 10:00 | 10:30 | 30 | 00:30 | 210 | 03:30 | TKT | Discussion for ticketing modification
17 | TKT | Note down table relations | Shareena/43432 | 1 | Shareena/43432/1 | TKT/Note down table relations | Shareena | 2018-11-28 | 10:32 | 16:52 | 380 | 06:20 | 380 | 06:20 | TKT | Note down table relations
18 | SDS | Decryption | Aswathy/43432 | 1 | Aswathy/43432/1 | SDS/Decryption | Aswathy | 2018-11-28 | 10:35 | 11:45 | 70 | 01:10 | 320 | 05:20 | SDS | Decryption
19 | RTM | Getting branchname into tool | Aswathy/43432 | 2 | Aswathy/43432/2 | RTM/Getting branchname into tool | Aswathy | 2018-11-28 | 12:15 | 12:45 | 30 | 00:30 | 320 | 05:20 | RTM | Getting branchname into tool
20 | SDS | Decryption | Aswathy/43432 | 3 | Aswathy/43432/3 | SDS/Decryption | Aswathy | 2018-11-28 | 12:45 | 16:25 | 220 | 03:40 | 320 | 05:20 | SDS | Decryption
21 | TKT | Note down table relations | Shareena/43433 | 1 | Shareena/43433/1 | TKT/Note down table relations | Shareena | 2018-11-29 | 11:05 | 13:15 | 130 | 02:10 | 250 | 04:10 | TKT | Note down table relations
22 | TKT | Entering table details into excel sheet | Shareena/43433 | 2 | Shareena/43433/2 | TKT/Entering table details into excel sheet | Shareena | 2018-11-29 | 13:45 | 15:45 | 120 | 02:00 | 250 | 04:10 | TKT | Entering table details into excel sheet
23 | SDS | Request and get Response from web | Aswathy/43434 | 1 | Aswathy/43434/1 | SDS/Request and get Response from web | Aswathy | 2018-11-30 | 9:20 | 13:08 | 228 | 03:48 | 423 | 07:03 | SDS | Request and get Response from web
24 | TKT | Entering table details into excel sheet | Shareena/43434 | 1 | Shareena/43434/1 | TKT/Entering table details into excel sheet | Shareena | 2018-11-30 | 9:45 | 13:10 | 205 | 03:25 | 390 | 06:30 | TKT | Entering table details into excel sheet
25 | SDS | Request and get Response from web | Aswathy/43434 | 2 | Aswathy/43434/2 | SDS/Request and get Response from web | Aswathy | 2018-11-30 | 13:45 | 17:00 | 195 | 03:15 | 423 | 07:03 | SDS | Request and get Response from web
26 | TKT | Entering table details into excel sheet | Shareena/43434 | 2 | Shareena/43434/2 | TKT/Entering table details into excel sheet | Shareena | 2018-11-30 | 13:45 | 15:50 | 125 | 02:05 | 390 | 06:30 | TKT | Entering table details into excel sheet
27 | TEEBPD | Inhouse Testing | Shareena/43434 | 3 | Shareena/43434/3 | TEEBPD/Inhouse Testing | Shareena | 2018-11-30 | 15:53 | 16:53 | 60 | 01:00 | 390 | 06:30 | TEEBPD | Inhouse Testing
28 | TEEBPD | Finalizing | Firose/43432 | 3 | Firose/43432/3 | TEEBPD/Finalizing | Firose | 2018-11-28 | 15:00 | 17:00 | 120 | 02:00 | 210 | 03:30 | TEEBPD | Finalizing
29 | TEEBPD | Finalizing | Firose/43433 | 1 | Firose/43433/1 | TEEBPD/Finalizing | Firose | 2018-11-29 | 10:00 | 17:00 | 420 | 07:00 | 420 | 07:00 | TEEBPD | Finalizing
30 | TEEBPD | Finalizing | Firose/43434 | 1 | Firose/43434/1 | TEEBPD/Finalizing | Firose | 2018-11-30 | 9:00 | 12:00 | 180 | 03:00 | 360 | 06:00 | TEEBPD | Finalizing
31 | TEEBPD | Inhouse Testing | Firose/43434 | 2 | Firose/43434/2 | TEEBPD/Inhouse Testing | Firose | 2018-11-30 | 14:00 | 17:00 | 180 | 03:00 | 360 | 06:00 | TEEBPD | Inhouse Testing
32 | TKT | Entering table details into excel sheet | Shareena/43435 | 1 | Shareena/43435/1 | TKT/Entering table details into excel sheet | Shareena | 2018-12-01 | 11:00 | 12:30 | 90 | 01:30 | 210 | 03:30 | TKT | Entering table details into excel sheet
33 | SDS | Request and get Response from web | Aswathy/43435 | 1 | Aswathy/43435/1 | SDS/Request and get Response from web | Aswathy | 2018-12-01 | 9:45 | 13:15 | 210 | 03:30 | 375 | 06:15 | SDS | Request and get Response from web
34 | SDS | Testing | Aswathy/43435 | 2 | Aswathy/43435/2 | SDS/Testing | Aswathy | 2018-12-01 | 13:40 | 14:00 | 20 | 00:20 | 375 | 06:15 | SDS | Testing
35 | SDS | Testing | Aswathy/43435 | 3 | Aswathy/43435/3 | SDS/Testing | Aswathy | 2018-12-01 | 14:35 | 15:40 | 65 | 01:05 | 375 | 06:15 | SDS | Testing
36 | SDS | Stage 2 | Aswathy/43435 | 4 | Aswathy/43435/4 | SDS/Stage 2 | Aswathy | 2018-12-01 | 15:40 | 17:00 | 80 | 01:20 | 375 | 06:15 | SDS | Stage 2
37 | TKT | Entering table details into excel sheet | Shareena/43435 | 2 | Shareena/43435/2 | TKT/Entering table details into excel sheet | Shareena | 2018-12-01 | 15:00 | 17:00 | 120 | 02:00 | 210 | 03:30 | TKT | Entering table details into excel sheet
38 | MITWEB | Modification | Firose/43435 | 1 | Firose/43435/1 | MITWEB/Modification | Firose | 2018-12-01 | 11:00 | 13:00 | 120 | 02:00 | 240 | 04:00 | MITWEB | Modification
39 | TEEBPD | Client Suggestion Implementation | Firose/43435 | 2 | Firose/43435/2 | TEEBPD/Client Suggestion Implementation | Firose | 2018-12-01 | 15:00 | 17:00 | 120 | 02:00 | 240 | 04:00 | TEEBPD | Client Suggestion Implementation
40 | SDS | Stage 2 | Aswathy/43437 | 1 | Aswathy/43437/1 | SDS/Stage 2 | Aswathy | 2018-12-03 | 9:45 | 11:45 | 120 | 02:00 | 353 | 05:53 | SDS | Stage 2
41 | SDS | Stage 2 | Aswathy/43437 | 2 | Aswathy/43437/2 | SDS/Stage 2 | Aswathy | 2018-12-03 | 12:10 | 13:10 | 60 | 01:00 | 353 | 05:53 | SDS | Stage 2
42 | SDS | Stage 2 | Aswathy/43437 | 3 | Aswathy/43437/3 | SDS/Stage 2 | Aswathy | 2018-12-03 | 13:35 | 14:58 | 83 | 01:23 | 353 | 05:53 | SDS | Stage 2
43 | SDS | Stage 2 | Aswathy/43437 | 4 | Aswathy/43437/4 | SDS/Stage 2 | Aswathy | 2018-12-03 | 15:30 | 17:00 | 90 | 01:30 | 353 | 05:53 | SDS | Stage 2
44 | TEEBPD | Synchronization Implementing | Firose/43437 | 1 | Firose/43437/1 | TEEBPD/Synchronization Implementing | Firose | 2018-12-03 | 9:00 | 17:00 | 480 | 08:00 | 480 | 08:00 | TEEBPD | Synchronization Implementing
45 | TKT | Entering table details into excel sheet | Shareena/43438 | 1 | Shareena/43438/1 | TKT/Entering table details into excel sheet | Shareena | 2018-12-04 | 9:30 | 12:00 | 150 | 02:30 | 150 | 02:30 | TKT | Entering table details into excel sheet
46 | SDS | Request and get Response from web | Aswathy/43438 | 1 | Aswathy/43438/1 | SDS/Request and get Response from web | Aswathy | 2018-12-04 | 9:30 | 12:00 | 150 | 02:30 | 150 | 02:30 | SDS | Request and get Response from web
47 | TKT | Package Creation-Stage1 | Shareena/43439 | 1 | Shareena/43439/1 | TKT/Package Creation-Stage1 | Shareena | 2018-12-05 | 13:30 | 16:30 | 180 | 03:00 | 180 | 03:00 | TKT | Package Creation-Stage1
48 | SDS | Request and get Response from web | Aswathy/43439 | 1 | Aswathy/43439/1 | SDS/Request and get Response from web | Aswathy | 2018-12-05 | 11:00 | 13:10 | 130 | 02:10 | 254 | 04:14 | SDS | Request and get Response from web
49 | SDS | Request and get Response from web | Aswathy/43439 | 2 | Aswathy/43439/2 | SDS/Request and get Response from web | Aswathy | 2018-12-05 | 15:00 | 17:04 | 124 | 02:04 | 254 | 04:14 | SDS | Request and get Response from web
50 | TKT | Package Creation-Stage1 | Shareena/43440 | 1 | Shareena/43440/1 | TKT/Package Creation-Stage1 | Shareena | 2018-12-06 | 11:00 | 13:00 | 120 | 02:00 | 120 | 02:00 | TKT | Package Creation-Stage1
51 | SDS | Request and get Response from web | Aswathy/43441 | 1 | Aswathy/43441/1 | SDS/Request and get Response from web | Aswathy | 2018-12-07 | 9:30 | 10:15 | 45 | 00:45 | 105 | 01:45 | SDS | Request and get Response from web
52 | TKT | Package Creation-Stage1 | Shareena/43441 | 1 | Shareena/43441/1 | TKT/Package Creation-Stage1 | Shareena | 2018-12-07 | 10:00 | 16:30 | 390 | 06:30 | 390 | 06:30 | TKT | Package Creation-Stage1
53 | TEEBPD | Client Suggestion Implementation | Firose/43438 | 1 | Firose/43438/1 | TEEBPD/Client Suggestion Implementation | Firose | 2018-12-04 | 10:00 | 18:00 | 480 | 08:00 | 480 | 08:00 | TEEBPD | Client Suggestion Implementation
54 | TEEBPD | Client Suggestion Implementation | Firose/43439 | 1 | Firose/43439/1 | TEEBPD/Client Suggestion Implementation | Firose | 2018-12-05 | 10:00 | 12:00 | 120 | 02:00 | 240 | 04:00 | TEEBPD | Client Suggestion Implementation
55 | TEEBPD | Finalizing | Firose/43439 | 2 | Firose/43439/2 | TEEBPD/Finalizing | Firose | 2018-12-05 | 14:00 | 16:00 | 120 | 02:00 | 240 | 04:00 | TEEBPD | Finalizing
56 | MITWEB | Modification | Firose/43441 | 1 | Firose/43441/1 | MITWEB/Modification | Firose | 2018-12-07 | 9:00 | 13:00 | 240 | 04:00 | 240 | 04:00 | MITWEB | Modification
57 | SDS | Modification | Aswathy/43441 | 2 | Aswathy/43441/2 | SDS/Modification | Aswathy | 2018-12-07 | 15:00 | 16:00 | 60 | 01:00 | 105 | 01:45 | SDS | Modification
58 | TKT | Package Creation-Stage1 | Shareena/43442 | 1 | Shareena/43442/1 | TKT/Package Creation-Stage1 | Shareena | 2018-12-08 | 10:00 | 12:46 | 166 | 02:46 | 251 | 04:11 | TKT | Package Creation-Stage1
59 | SDS | Modification | Aswathy/43442 | 1 | Aswathy/43442/1 | SDS/Modification | Aswathy | 2018-12-08 | 10:00 | 14:00 | 240 | 04:00 | 240 | 04:00 | SDS | Modification
60 | TKT | Package Creation-Stage1 | Shareena/43442 | 2 | Shareena/43442/2 | TKT/Package Creation-Stage1 | Shareena | 2018-12-08 | 14:15 | 15:00 | 45 | 00:45 | 251 | 04:11 | TKT | Package Creation-Stage1
61 | TKT | Package Creation-Stage1 | Shareena/43442 | 3 | Shareena/43442/3 | TKT/Package Creation-Stage1 | Shareena | 2018-12-08 | 16:15 | 16:55 | 40 | 00:40 | 251 | 04:11 | TKT | Package Creation-Stage1
62 | TKT | Package Creation-Stage1 | Shareena/43444 | 1 | Shareena/43444/1 | TKT/Package Creation-Stage1 | Shareena | 2018-12-10 | 9:15 | 12:00 | 165 | 02:45 | 315 | 05:15 | TKT | Package Creation-Stage1
63 | TKT | Package Creation-Stage1 | Shareena/43444 | 2 | Shareena/43444/2 | TKT/Package Creation-Stage1 | Shareena | 2018-12-10 | 14:00 | 16:30 | 150 | 02:30 | 315 | 05:15 | TKT | Package Creation-Stage1
64 | TKT | Package Creation-Stage2(Resource creation) | Shareena/43445 | 1 | Shareena/43445/1 | TKT/Package Creation-Stage2(Resource creation) | Shareena | 2018-12-11 | 9:30 | 12:15 | 165 | 02:45 | 165 | 02:45 | TKT | Package Creation-Stage2(Resource creation)
65 | APPFRAME | Development | Firose/43444 | 1 | Firose/43444/1 | APPFRAME/Development | Firose | 2018-12-10 | 9:00 | 17:00 | 480 | 08:00 | 480 | 08:00 | APPFRAME | Development
66 | SDS | Modification | Aswathy/43445 | 1 | Aswathy/43445/1 | SDS/Modification | Aswathy | 2018-12-11 | 12:45 | 13:25 | 40 | 00:40 | 220 | 03:40 | SDS | Modification
67 | SDS | Modification | Aswathy/43445 | 2 | Aswathy/43445/2 | SDS/Modification | Aswathy | 2018-12-11 | 14:00 | 17:00 | 180 | 03:00 | 220 | 03:40 | SDS | Modification
68 | TEEBPD | Table syncing | Shareena/43446 | 1 | Shareena/43446/1 | TEEBPD/Table syncing | Shareena | 2018-12-12 | 9:50 | 11:00 | 70 | 01:10 | 182 | 03:02 | TEEBPD | Table syncing
69 | SDS | Modification | Aswathy/43446 | 1 | Aswathy/43446/1 | SDS/Modification | Aswathy | 2018-12-12 | 9:30 | 13:30 | 240 | 04:00 | 405 | 06:45 | SDS | Modification
70 | TEEBPD | Table syncing | Shareena/43446 | 2 | Shareena/43446/2 | TEEBPD/Table syncing | Shareena | 2018-12-12 | 15:05 | 16:57 | 112 | 01:52 | 182 | 03:02 | TEEBPD | Table syncing
71 | SDS | Modification | Aswathy/43446 | 2 | Aswathy/43446/2 | SDS/Modification | Aswathy | 2018-12-12 | 14:10 | 16:55 | 165 | 02:45 | 405 | 06:45 | SDS | Modification
72 | SDS | Modification | Aswathy/43447 | 1 | Aswathy/43447/1 | SDS/Modification | Aswathy | 2018-12-13 | 9:20 | 12:10 | 170 | 02:50 | 170 | 02:50 | SDS | Modification
73 | TKT | Package Creation-Stage2(Resource creation) | Shareena/43447 | 1 | Shareena/43447/1 | TKT/Package Creation-Stage2(Resource creation) | Shareena | 2018-12-13 | 9:30 | 16:55 | 445 | 07:25 | 445 | 07:25 | TKT | Package Creation-Stage2(Resource creation)
74 | TEEBPD | Table syncing | Shareena/43448 | 1 | Shareena/43448/1 | TEEBPD/Table syncing | Shareena | 2018-12-14 | 11:30 | 13:00 | 90 | 01:30 | 265 | 04:25 | TEEBPD | Table syncing
75 | SDS | Testing | Aswathy/43448 | 1 | Aswathy/43448/1 | SDS/Testing | Aswathy | 2018-12-14 | 10:15 | 13:10 | 175 | 02:55 | 220 | 03:40 | SDS | Testing
76 | SDS | Testing | Aswathy/43448 | 2 | Aswathy/43448/2 | SDS/Testing | Aswathy | 2018-12-14 | 13:45 | 14:30 | 45 | 00:45 | 220 | 03:40 | SDS | Testing
77 | TEEBPD | Table syncing | Shareena/43448 | 2 | Shareena/43448/2 | TEEBPD/Table syncing | Shareena | 2018-12-14 | 14:00 | 16:55 | 175 | 02:55 | 265 | 04:25 | TEEBPD | Table syncing
78 | TEEBPD | Table syncing | Shareena/43449 | 1 | Shareena/43449/1 | TEEBPD/Table syncing | Shareena | 2018-12-15 | 10:00 | 17:00 | 420 | 07:00 | 420 | 07:00 | TEEBPD | Table syncing
78 | SDS | Testing | Aswathy/43449 | 1 | Aswathy/43449/1 | SDS/Testing | Aswathy | 2018-12-15 | 9:15 | 10:20 | 65 | 01:05 | 255 | 04:15 | SDS | Testing
79 | RTM | Modification | Aswathy/43449 | 2 | Aswathy/43449/2 | RTM/Modification | Aswathy | 2018-12-15 | 13:20 | 16:30 | 190 | 03:10 | 255 | 04:15 | RTM | Modification
80 | TEEBPD | Table syncing | Shareena/43451 | 1 | Shareena/43451/1 | TEEBPD/Table syncing | Shareena | 2018-12-17 | 9:30 | 13:00 | 210 | 03:30 | 390 | 06:30 | TEEBPD | Table syncing
81 | TEEBPD | Table syncing | Shareena/43451 | 2 | Shareena/43451/2 | TEEBPD/Table syncing | Shareena | 2018-12-17 | 14:00 | 17:00 | 180 | 03:00 | 390 | 06:30 | TEEBPD | Table syncing
82 | TEEBPD | Table syncing | Shareena/43452 | 1 | Shareena/43452/1 | TEEBPD/Table syncing | Shareena | 2018-12-18 | 9:15 | 16:00 | 405 | 06:45 | 405 | 06:45 | TEEBPD | Table syncing
83 | TEEBPD | Table syncing | Shareena/43453 | 1 | Shareena/43453/1 | TEEBPD/Table syncing | Shareena | 2018-12-19 | 9:30 | 15:00 | 330 | 05:30 | 330 | 05:30 | TEEBPD | Table syncing
84 | RTM | Modification | Aswathy/43451 | 1 | Aswathy/43451/1 | RTM/Modification | Aswathy | 2018-12-17 | 9:30 | 10:30 | 60 | 01:00 | 60 | 01:00 | RTM | Modification
85 | SDS | Testing | Aswathy/43452 | 1 | Aswathy/43452/1 | SDS/Testing | Aswathy | 2018-12-18 | 11:00 | 13:00 | 120 | 02:00 | 120 | 02:00 | SDS | Testing
86 | RTM | Modification | Aswathy/43453 | 1 | Aswathy/43453/1 | RTM/Modification | Aswathy | 2018-12-19 | 9:00 | 11:00 | 120 | 02:00 | 300 | 05:00 | RTM | Modification
87 | RTM | Modification | Aswathy/43453 | 2 | Aswathy/43453/2 | RTM/Modification | Aswathy | 2018-12-19 | 14:00 | 17:00 | 180 | 03:00 | 300 | 05:00 | RTM | Modification
88 | RTM | Modification | Aswathy/43454 | 1 | Aswathy/43454/1 | RTM/Modification | Aswathy | 2018-12-20 | 9:15 | 11:15 | 120 | 02:00 | 120 | 02:00 | RTM | Modification
89 | SDS | Modification | Aswathy/43455 | 1 | Aswathy/43455/1 | SDS/Modification | Aswathy | 2018-12-21 | 14:00 | 16:30 | 150 | 02:30 | 150 | 02:30 | SDS | Modification
90 | TEEBPD | Table syncing | Shareena/43454 | 1 | Shareena/43454/1 | TEEBPD/Table syncing | Shareena | 2018-12-20 | 10:00 | 16:00 | 360 | 06:00 | 360 | 06:00 | TEEBPD | Table syncing
91 | TEEBPD | Table syncing | Shareena/43455 | 1 | Shareena/43455/1 | TEEBPD/Table syncing | Shareena | 2018-12-21 | 10:30 | 15:30 | 300 | 05:00 | 300 | 05:00 | TEEBPD | Table syncing
92 | SDS | Modification | Aswathy/43456 | 1 | Aswathy/43456/1 | SDS/Modification | Aswathy | 2018-12-22 | 9:15 | 13:10 | 235 | 03:55 | 295 | 04:55 | SDS | Modification
93 | SDS | Testing | Aswathy/43456 | 2 | Aswathy/43456/2 | SDS/Testing | Aswathy | 2018-12-22 | 15:30 | 16:30 | 60 | 01:00 | 295 | 04:55 | SDS | Testing
94 | TEEBPD | Table syncing | Shareena/43458 | 1 | Shareena/43458/1 | TEEBPD/Table syncing | Shareena | 2018-12-24 | 9:30 | 13:00 | 210 | 03:30 | 330 | 05:30 | TEEBPD | Table syncing
95 | TEEBPD | Table syncing | Shareena/43458 | 2 | Shareena/43458/2 | TEEBPD/Table syncing | Shareena | 2018-12-24 | 15:00 | 17:00 | 120 | 02:00 | 330 | 05:30 | TEEBPD | Table syncing
96 | TEEBPD | Table syncing | Shareena/43461 | 1 | Shareena/43461/1 | TEEBPD/Table syncing | Shareena | 2018-12-27 | 14:30 | 17:00 | 150 | 02:30 | 150 | 02:30 | TEEBPD | Table syncing
97 | SDS | Error Correction | Aswathy/43465 | 1 | Aswathy/43465/1 | SDS/Error Correction | Aswathy | 2018-12-31 | 14:00 | 17:00 | 180 | 03:00 | 180 | 03:00 | SDS | Error Correction
98 | SDS | Error Correction | Aswathy/43466 | 1 | Aswathy/43466/1 | SDS/Error Correction | Aswathy | 2019-01-01 | 9:15 | 10:00 | 45 | 00:45 | 200 | 03:20 | SDS | Error Correction
99 | SDS | Testing | Aswathy/43466 | 2 | Aswathy/43466/2 | SDS/Testing | Aswathy | 2019-01-01 | 10:00 | 10:20 | 20 | 00:20 | 200 | 03:20 | SDS | Testing
100 | SDS | Modification | Aswathy/43466 | 3 | Aswathy/43466/3 | SDS/Modification | Aswathy | 2019-01-01 | 14:00 | 15:30 | 90 | 01:30 | 200 | 03:20 | SDS | Modification
101 | SDS | Modification | Aswathy/43466 | 4 | Aswathy/43466/4 | SDS/Modification | Aswathy | 2019-01-01 | 16:15 | 17:00 | 45 | 00:45 | 200 | 03:20 | SDS | Modification
102 | SDS | Modification | Aswathy/43467 | 1 | Aswathy/43467/1 | SDS/Modification | Aswathy | 2019-01-02 | 9:15 | 11:20 | 125 | 02:05 | 215 | 03:35 | SDS | Modification
103 | SDS | Testing | Aswathy/43467 | 2 | Aswathy/43467/2 | SDS/Testing | Aswathy | 2019-01-02 | 12:00 | 13:30 | 90 | 01:30 | 215 | 03:35 | SDS | Testing
104 | SDS | Modification | Aswathy/43469 | 1 | Aswathy/43469/1 | SDS/Modification | Aswathy | 2019-01-04 | 16:00 | 17:00 | 60 | 01:00 | 60 | 01:00 | SDS | Modification
105 | SDS | Modification | Aswathy/43477 | 1 | Aswathy/43477/1 | SDS/Modification | Aswathy | 2019-01-12 | 14:00 | 15:00 | 60 | 01:00 | 60 | 01:00 | SDS | Modification
106 | SDS | Modification | Aswathy/43479 | 1 | Aswathy/43479/1 | SDS/Modification | Aswathy | 2019-01-14 | 13:00 | 14:00 | 60 | 01:00 | 165 | 02:45 | SDS | Modification
107 | SDS | Modification | Aswathy/43479 | 2 | Aswathy/43479/2 | SDS/Modification | Aswathy | 2019-01-14 | 15:00 | 16:00 | 60 | 01:00 | 165 | 02:45 | SDS | Modification
108 | SDS | Testing | Aswathy/43479 | 3 | Aswathy/43479/3 | SDS/Testing | Aswathy | 2019-01-14 | 16:00 | 16:45 | 45 | 00:45 | 165 | 02:45 | SDS | Testing
109 | SDS | Testing | Aswathy/43480 | 1 | Aswathy/43480/1 | SDS/Testing | Aswathy | 2019-01-15 | 9:30 | 11:00 | 90 | 01:30 | 90 | 01:30 | SDS | Testing
110 | TEEBPD | Table syncing | Shareena/43480 | 1 | Shareena/43480/1 | TEEBPD/Table syncing | Shareena | 2019-01-15 | 10:00 | 13:00 | 180 | 03:00 | 180 | 03:00 | TEEBPD | Table syncing
111 | TEEBPD | Table syncing | Shareena/43486 | 1 | Shareena/43486/1 | TEEBPD/Table syncing | Shareena | 2019-01-21 | 9:30 | 15:00 | 330 | 05:30 | 330 | 05:30 | TEEBPD | Table syncing
111 | TEEBPD | Table syncing | Shareena/43489 | 1 | Shareena/43489/1 | TEEBPD/Table syncing | Shareena | 2019-01-24 | 16:00 | 17:00 | 60 | 01:00 | 60 | 01:00 | TEEBPD | Table syncing
112 | TEEBPD | Table syncing | Vishnu/43516 | 1 | Vishnu/43516/1 | TEEBPD/Table syncing | Vishnu | 2019-02-20 | 12:36 | 15:00 | 144 | 02:24 | 144 | 02:24 | TEEBPD | Table syncing
113 | TEEBPD | Table syncing | Vishnu/43521 | 1 | Vishnu/43521/1 | TEEBPD/Table syncing | Vishnu | 2019-02-25 | 10:00 | 13:30 | 210 | 03:30 | 210 | 03:30 | TEEBPD | Table syncing
114 | TEEBPD | Table syncing | Vishnu/43522 | 1 | Vishnu/43522/1 | TEEBPD/Table syncing | Vishnu | 2019-02-26 | 12:00 | 16:00 | 240 | 04:00 | 240 | 04:00 | TEEBPD | Table syncing
115 | TEEBPD | Table syncing | Vishnu/43523 | 1 | Vishnu/43523/1 | TEEBPD/Table syncing | Vishnu | 2019-02-27 | 9:30 | 13:00 | 210 | 03:30 | 300 | 05:00 | TEEBPD | Table syncing
116 | TEEBPD | Table syncing | Vishnu/43523 | 2 | Vishnu/43523/2 | TEEBPD/Table syncing | Vishnu | 2019-02-27 | 14:00 | 15:30 | 90 | 01:30 | 300 | 05:00 | TEEBPD | Table syncing
117 | TEEBPD | Table syncing | Vishnu/43524 | 1 | Vishnu/43524/1 | TEEBPD/Table syncing | Vishnu | 2019-02-28 | 11:30 | 17:00 | 330 | 05:30 | 330 | 05:30 | TEEBPD | Table syncing
118 | TEEBPD | Table syncing | Vishnu/43525 | 1 | Vishnu/43525/1 | TEEBPD/Table syncing | Vishnu | 2019-03-01 | 10:00 | 15:30 | 330 | 05:30 | 330 | 05:30 | TEEBPD | Table syncing
119 | TEEBPD | Table syncing | Vishnu/43526 | 1 | Vishnu/43526/1 | TEEBPD/Table syncing | Vishnu | 2019-03-02 | 10:00 | 14:00 | 240 | 04:00 | 240 | 04:00 | TEEBPD | Table syncing
120 | TEEBPD | Table syncing | Vishnu/43529 | 1 | Vishnu/43529/1 | TEEBPD/Table syncing | Vishnu | 2019-03-05 | 9:30 | 12:00 | 150 | 02:30 | 270 | 04:30 | TEEBPD | Table syncing
121 | TEEBPD | Table syncing | Vishnu/43529 | 2 | Vishnu/43529/2 | TEEBPD/Table syncing | Vishnu | 2019-03-05 | 13:00 | 15:00 | 120 | 02:00 | 270 | 04:30 | TEEBPD | Table syncing
122 | TEEBPD | Table syncing | Vishnu/43530 | 1 | Vishnu/43530/1 | TEEBPD/Table syncing | Vishnu | 2019-03-06 | 9:30 | 14:00 | 270 | 04:30 | 270 | 04:30 | TEEBPD | Table syncing
123 | AMC | Documentation | Aswathy/43521 | 1 | Aswathy/43521/1 | AMC/Documentation | Aswathy | 2019-02-25 | 9:30 | 11:30 | 120 | 02:00 | 120 | 02:00 | AMC | Documentation
124 | AMC | Documentation | Aswathy/43522 | 1 | Aswathy/43522/1 | AMC/Documentation | Aswathy | 2019-02-26 | 9:30 | 10:30 | 60 | 01:00 | 60 | 01:00 | AMC | Documentation
125 | TEEBPD | Table syncing | Vishnu/43531 | 1 | Vishnu/43531/1 | TEEBPD/Table syncing | Vishnu | 2019-03-07 | 10:00 | 15:00 | 300 | 05:00 | 300 | 05:00 | TEEBPD | Table syncing
126 | TEEBPD | Table syncing | Vishnu/43532 | 1 | Vishnu/43532/1 | TEEBPD/Table syncing | Vishnu | 2019-03-08 | 9:30 | 14:30 | 300 | 05:00 | 300 | 05:00 | TEEBPD | Table syncing
127 | TEEBPD | Table syncing | Vishnu/43533 | 1 | Vishnu/43533/1 | TEEBPD/Table syncing | Vishnu | 2019-03-09 | 9:00 | 15:30 | 390 | 06:30 | 390 | 06:30 | TEEBPD | Table syncing
128 | TEEBPD | Table syncing | Vishnu/43535 | 1 | Vishnu/43535/1 | TEEBPD/Table syncing | Vishnu | 2019-03-11 | 9:30 | 13:00 | 210 | 03:30 | 210 | 03:30 | TEEBPD | Table syncing
129 | TEEBPD | Table syncing | Vishnu/43536 | 1 | Vishnu/43536/1 | TEEBPD/Table syncing | Vishnu | 2019-03-12 | 10:00 | 16:00 | 360 | 06:00 | 360 | 06:00 | TEEBPD | Table syncing
130 | TEEBPD | Table syncing | Vishnu/43537 | 1 | Vishnu/43537/1 | TEEBPD/Table syncing | Vishnu | 2019-03-13 | 10:00 | 15:00 | 300 | 05:00 | 300 | 05:00 | TEEBPD | Table syncing
131 | TEEBPD | Table syncing | Vishnu/43538 | 1 | Vishnu/43538/1 | TEEBPD/Table syncing | Vishnu | 2019-03-14 | 9:30 | 23:00 | 810 | 13:30 | 900 | 15:00 | TEEBPD | Table syncing
132 | TEEBPD | Table syncing | Vishnu/43538 | 2 | Vishnu/43538/2 | TEEBPD/Table syncing | Vishnu | 2019-03-14 | 14:00 | 15:30 | 90 | 01:30 | 900 | 15:00 | TEEBPD | Table syncing
133 | TEEBPD | Table syncing | Vishnu/43539 | 1 | Vishnu/43539/1 | TEEBPD/Table syncing | Vishnu | 2019-03-15 | 10:00 | 16:00 | 360 | 06:00 | 360 | 06:00 | TEEBPD | Table syncing
134 | TEEBPD | Table syncing | Vishnu/43540 | 1 | Vishnu/43540/1 | TEEBPD/Table syncing | Vishnu | 2019-03-16 | 11:00 | 13:00 | 120 | 02:00 | 120 | 02:00 | TEEBPD | Table syncing
135 | TEEBPD | Table syncing | Vishnu/43542 | 1 | Vishnu/43542/1 | TEEBPD/Table syncing | Vishnu | 2019-03-18 | 10:00 | 11:00 | 60 | 01:00 | 120 | 02:00 | TEEBPD | Table syncing
136 | TEEBPD | Table syncing | Vishnu/43542 | 2 | Vishnu/43542/2 | TEEBPD/Table syncing | Vishnu | 2019-03-18 | 15:00 | 16:00 | 60 | 01:00 | 120 | 02:00 | TEEBPD | Table syncing
137 | TEEBPD | Table syncing | Vishnu/43543 | 1 | Vishnu/43543/1 | TEEBPD/Table syncing | Vishnu | 2019-03-19 | 12:00 | 16:00 | 240 | 04:00 | 240 | 04:00 | TEEBPD | Table syncing
138 | TEEBPD | Table syncing | Vishnu/43545 | 1 | Vishnu/43545/1 | TEEBPD/Table syncing | Vishnu | 2019-03-21 | 10:00 | 14:00 | 240 | 04:00 | 240 | 04:00 | TEEBPD | Table syncing
139 | TEEBPD | Table syncing | Vishnu/43546 | 1 | Vishnu/43546/1 | TEEBPD/Table syncing | Vishnu | 2019-03-22 | 11:00 | 14:30 | 210 | 03:30 | 210 | 03:30 | TEEBPD | Table syncing
140 | RTRDB | Documentation | Aswathy/43542 | 1 | Aswathy/43542/1 | RTRDB/Documentation | Aswathy | 2019-03-18 | 10:00 | 12:10 | 130 | 02:10 | 130 | 02:10 | RTRDB | Documentation
141 | RTRDB | Documentation | Aswathy/43543 | 1 | Aswathy/43543/1 | RTRDB/Documentation | Aswathy | 2019-03-19 | 15:00 | 16:00 | 60 | 01:00 | 60 | 01:00 | RTRDB | Documentation
142 | RTRDB | Surrender PC | Aswathy/43545 | 1 | Aswathy/43545/1 | RTRDB/Surrender PC | Aswathy | 2019-03-21 | 15:00 | 17:00 | 120 | 02:00 | 120 | 02:00 | RTRDB | Surrender PC
143 | RTRDB | Surrender PC | Aswathy/43546 | 1 | Aswathy/43546/1 | RTRDB/Surrender PC | Aswathy | 2019-03-22 | 9:30 | 12:30 | 180 | 03:00 | 320 | 05:20 | RTRDB | Surrender PC
144 | RTRDB | Surrender PC | Aswathy/43546 | 2 | Aswathy/43546/2 | RTRDB/Surrender PC | Aswathy | 2019-03-22 | 14:00 | 15:15 | 75 | 01:15 | 320 | 05:20 | RTRDB | Surrender PC
145 | RTRDB | Surrender PC | Aswathy/43546 | 3 | Aswathy/43546/3 | RTRDB/Surrender PC | Aswathy | 2019-03-22 | 15:45 | 16:50 | 65 | 01:05 | 320 | 05:20 | RTRDB | Surrender PC
146 | TEEBPD | Table syncing | Vishnu/43547 | 1 | Vishnu/43547/1 | TEEBPD/Table syncing | Vishnu | 2019-03-23 | 9:15 | 13:00 | 225 | 03:45 | 225 | 03:45 | TEEBPD | Table syncing
147 | RTRDB | Surrender PC | Aswathy/43547 | 1 | Aswathy/43547/1 | RTRDB/Surrender PC | Aswathy | 2019-03-23 | 9:30 | 13:30 | 240 | 04:00 | 240 | 04:00 | RTRDB | Surrender PC
148 | RTRDB | Restore DB | Aswathy/43549 | 1 | Aswathy/43549/1 | RTRDB/Restore DB | Aswathy | 2019-03-25 | 10:00 | 13:30 | 210 | 03:30 | 210 | 03:30 | RTRDB | Restore DB
149 | RTRDB | Restore DB | Aswathy/43550 | 1 | Aswathy/43550/1 | RTRDB/Restore DB | Aswathy | 2019-03-26 | 15:00 | 16:30 | 90 | 01:30 | 90 | 01:30 | RTRDB | Restore DB
150 | RTRDB | Restore DB | Aswathy/43551 | 1 | Aswathy/43551/1 | RTRDB/Restore DB | Aswathy | 2019-03-27 | 9:30 | 13:00 | 210 | 03:30 | 255 | 04:15 | RTRDB | Restore DB
151 | RTRDB | Restore DB | Aswathy/43551 | 2 | Aswathy/43551/2 | RTRDB/Restore DB | Aswathy | 2019-03-27 | 16:00 | 16:45 | 45 | 00:45 | 255 | 04:15 | RTRDB | Restore DB
152 | RTRDB | Restore DB | Aswathy/43553 | 1 | Aswathy/43553/1 | RTRDB/Restore DB | Aswathy | 2019-03-29 | 14:00 | 17:00 | 180 | 03:00 | 180 | 03:00 | RTRDB | Restore DB

## Project Report
Restore Database
Employee Wise Timing
RTRDB |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Seq | Tasks |  | Total Time | Aswathy | Vishnu | Shareena | Firose
1 | Documentation |  | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0
2 | Surrender PC |  | 680 | 680 | 0 | 0 | 0 | 0 | 0 | 0
3 | Restore DB |  | 735 | 735 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 1605 | 1605 | 0 | 0 | 0 | 0 | 0 | 0

## Employee Timing Report
Aswathy |  |  | Start Date |  | Minutes | Hours
|  |  | 2019-01-10 |  | 315 | 5:15
Project Wise Timing
6 Day Report
1 | [6 empty] | No | Project |  | Minutes
2 | 2019-01-10 |  |  | 0 | 0 |  | 1 | SDS |  | 315 |  |  | 0 | [6 empty] | 0
3 |  |  |  | 0 |  |  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0
4 |  |  |  | 0 |  |  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0
1 |  |  |  | 0 |  |  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0
2 | 2019-01-11 |  |  | 0 | 0 |  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0
3 |  |  |  | 0 | [8 empty] | 0 | [6 empty] | 0
4 |  |  |  | 0 |  |  | Project Task Wise Timing | [5 empty] | 0 | [6 empty] | 0
1 |  |  |  | 0 | [8 empty] | 0 | [6 empty] | 0
2 | 2019-01-12 | SDS/Modification |  | 60 | 60 |  | Project |  | Tasks |  | Task Time | Total | 1 | SDS | 1 | 1 | SDS | SDS/1 | Modification | 180
3 |  |  |  | 0 |  | 1 | SDS |  | Modification |  | 180 | 315 | 0 | [6 empty] | 0
4 |  |  |  | 0 |  | 2 |  |  | Testing |  | 135 |  | 0 | [6 empty] | 0
1 |  |  |  | 0 |  | 3 | [6 empty] | 0 | [6 empty] | 0
2 | 2019-01-13 |  |  | 0 | 0 | 4 | [6 empty] | 0 | [6 empty] | 0
3 |  |  |  | 0 |  | 1 | [5 empty] | 0 | 0 | [6 empty] | 0
4 |  |  |  | 0 |  | 2 | [6 empty] | 0 | [6 empty] | 0
1 |  |  |  | 0 |  | 3 | [6 empty] | 0 | [6 empty] | 0
2 | 2019-01-14 | SDS/Modification |  | 60 | 165 | 4 | [6 empty] | 0 | [6 empty] | 0
3 |  | SDS/Modification |  | 60 |  | 1 | [5 empty] | 0 | 0 | [6 empty] | 0
4 |  | SDS/Testing |  | 45 |  | 2 | [6 empty] | 1 | SDS | 2 |  | SDS | SDS/2 | Testing | 135
1 |  |  |  | 0 |  | 3 | [6 empty] | 0 | [6 empty] | 0
2 | 2019-01-15 | SDS/Testing |  | 90 | 90 | 4 | [6 empty] | 0 | [6 empty] | 0
3 |  |  |  | 0 |  | 1 | [5 empty] | 0 | 0 | [6 empty] | 0
4 |  |  |  | 0 |  | 2 | [6 empty] | 0 | [6 empty] | 0
|  |  |  | 0 |  | 3 | [6 empty] | 0 | [6 empty] | 0
4
[6 empty] | 1 | [5 empty] | 0
2
3
4